## Title_Page
| Minutes of Meeting |  |  | Doc Number : ICP-MOM-PR1481 Revision : 01 Last Modified : 29 Jun 2021
Customer | CLIENT NAME
Project Code / Name | PROJECT NAME
Meeting Date | Meeting Location | Meeting Attendees (Company/Dept) | Agenda/Purpose | Meeting Notes Prepared By
2021-06-22 | Google Hangout | Attendees List | Kick Off Meeting for Project Name 1. Safety Introduction 2. Project Architecture 3. Project Scope 4. Proposed Control BOM 5. Deliverable Documents 6. Project Schedule 7. Project Organization Chart 8. Discussion Points | Udhaya Kumar S (IC Pro)
2021-06-29 | Google Hangout | Attendees List | Project Progress Meeting | Udhaya Kumar S (IC Pro)

## MOM_Points
Minutes of Meeting | [6 empty] | Doc Number : ICP-MOM-PR1481 Revision : 01 Last Modified : 29 Jun 2021
Item No | Discussion Points | MOM Date | Action By | Due Date | Completion Date | Status | Remarks
1 | Final I/O List including I/O Type, I/O assignment with grouping requirements (if any) shall be provided by ALSG | 2021-06-22 | ALSG | 2021-06-24 | 2021-06-22 | Completed | 22 Jun 2021 ICPro : As discussed in KOM, ALSG mentioned ICPro can assign the IO's in the order listed in IO List
2 | Control Philosophy, C&E, Functional requirements, Instrument Engineering range, Setpoints to be provided by ALSG | 2021-06-22 | ALSG | 2021-06-30 | 2021-06-24 | Completed | C&E not applicable for this system
3 | Installation location of panel in AMK-2; any space constrain for the panel | 2021-06-22 | ALSG | 2021-06-24 | 2021-06-22 | Completed | 22 Jun 2021 ICPro : As discussed in KOM, ALSG replied they don't have any space/panel size constrain; new panel can be floor mount/wall mount based on the ICPro design considerations and panel will be installed in the AMK-02 meeting room near to the analyser panel. Cable entry to the panel shall be bottom entry.
4 | ICPro will review and submit the Panel GA/IGA, BOM document by 25 Jun 2021 for ALSG review and approval | 2021-06-22 | IC Pro | 2021-06-25 | 2021-06-26 | Completed
5 | Document review and approval by ALSG to be completed within 3 working days of ICPro document submission as the project is on tight schedule; If required Alsg may call for a meeting to clarify any points. Alsg shall collate comments from different Stakeholders in Alsg and provide consolidated comments at once. | 2021-06-22 | ICPro/ALSG | - | - | Info
6 | Point of Contact at ALSG for Project Communication – Progress, Meeting, document submission etc. ALSG will share the details to ICPro | 2021-06-22 | ALSG | 2021-06-23 | 2021-06-23 | Completed | 22 Jun 2021 ICPro : Mr. Nidheesh (ALSG) has shared the ALSG team e-mail addresses through mail for project communication
7 | Project Progress Meeting will be conducted on every Tuesday at 02:00 PM to 03:00PM | 2021-06-22 | ICPro/ALSG | - | - | Info
8 | IC Pro highlighted that design freeze and providing final Input from ALSG is in critical path of the project. Any changes in later date may have impact on the project schedule | 2021-06-22 | ALSG | - | - | Info
9 | IC Pro presented the KOM slides which included scope of work, high level schedule, document deliverable list, project organization chart and discussed above points. Refer attached copy of the KOM presentation for reference. | 2021-06-22 | ALSG | - | - | Info
10 | ALSG requested ICPro to submit the Logic Diagram with FDS submission, where logic diagram is not part of deliverable documents by ICPro and Mr. Nidheesh(ALSG) will prepare and submit the logic diagram document internally to ALSG | 2021-06-29 | ALSG | - | - | Info
11 | ALSG requested ICPro to review the Operation And Control Philosophy shared by ALSG and revert back with the comments/ clarification list to ALSG | 2021-06-29 | ICPro | 2021-07-03 |  | In Progress
12 | ALSG disucssed for the redundant SCADA requirement in the meeting, disucssed with ALSG reliability and Instrumentation team and concluded to add the AMK-02 TCN6200 Cooling Tower System Screen in AMK-03 existing SCADA(HIS-03, HIS-04). SCADA PC supplied in this project will be used for Installation and Commissioning of TCN6200 Cooling Tower System independently without disturbing the other system (AMK-03 LNG & Utility System) and later Screens, Tags, Alarms Logging, Tag Logging congifuration will be imported to AMK-03 existing SCADA(HIS-03, HIS-04) based on both ALSG/ICPro approval and confirmation. ALSG will dicuss with ICPro Sales and Support team for addition of AMK-02 TCN6200 Cooling Tower System Screen in AMK-03 existing SCADA(HIS-03, HIS-04) and engineering work for addition of Screens, Tags, Alarms Logging, Tag Logging congifuration will be carried out by ICPro based on both ALSG/ICPro approval and Confirmation. | 2021-06-29 | ALSG/ICPro | - | - | Info