## Frontpage
Project Code Project Name Project Plan
ISSUED FOR REVIEW |  | A |  | 21.09.2020 | ANP | RV | RV
REASON FOR ISSUE |  | REVISION |  | REV. DATE | PREP. BY | CHECKED | APPROVED
|  |  | Document Family: |  | LIST |  | No. of pages:
2
Project: | Project Name
Location | Location
Client: | Client Name
Document Title: Project Plan / Schedule
Client Doc. No: |  |  | Doc. No.: |  |  |  | Rev. :
|  |  | ICP_PR_XXXX_ProjectName_PPS |  |  |  | A

## Revision Notes
Rev | Dates | Descriptions

## Plan
Project Code / Name | [6 empty] | Last Updated
Project Start Date |  | 2020-06-09 |  |  |  |  | Revision
Project Manager |  | Mr.
WBS | TASK | RESPONSIBILITY | PLANNED START | PLANNED END | ACTUAL END | Engineer | DAYS | % DONE | Remark
1 | Project Kick OFF | --- | 2020-06-02 | 2020-06-02 | --- |  | 1 | 0%
1.1 | Project Kick OFF | IC Pro/CustomerName | 2020-06-02 | 2020-06-02 | 2020-06-02 |  | 1 | 100%
2 | Customer Document Supply | --- | 2020-06-10 | 2020-06-12 | --- |  | 3 | 0%
2.1 | IO Details for Preparation of IO List and Panel Drawings | IC Pro/CustomerName | 2020-06-10 | 2020-06-10 |  |  | 1 | 0%
2.2 | Existing SCADA Backups of AMK1 & AMK2, Cold Embrittlement | IC Pro/CustomerName | 2020-06-10 | 2020-06-10 | 2020-06-15 |  | 1 | 100%
2.3 | Existing Panel Termination Drawing | IC Pro/CustomerName | 2020-06-10 | 2020-06-11 |  |  | 2 | 60%
2.4 | SCADA/PLC Control Philosophy Document for Development | IC Pro/CustomerName | 2020-06-10 | 2020-06-12 |  |  | 3 | 0%
3 | Key Documents Submission | --- | 2020-06-09 | 2020-07-24 | --- |  | 15 | 0%
3.1 | Project Plan | IC Pro | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | 1 | 100%
3.2 | Control BOM | IC Pro | 2020-06-09 | 2020-06-09 | 2020-06-19 |  | 1 | 100%
3.3 | Electrical BOM | IC Pro | 2020-06-11 | 2020-06-12 |  |  | 2 | 40%
3.4 | Datasheets | IC Pro | 2020-06-11 | 2020-06-12 | 2020-06-19 |  | 2 | 100%
3.2 | Panel GA/IGA Drawings | IC Pro | 2020-06-09 | 2020-06-15 | 2020-06-25 |  | 7 | 40%
3.5 | Network Architecture | IC Pro | 2020-06-22 | 2020-06-23 | 2020-06-25 |  | 2 | 0%
4 | Other Documents Submission | --- | 2020-06-10 | 2020-07-24 | --- |  | 15 | 0%
4.1 | Electrical Panel Drawings | IC Pro | 2020-06-15 | 2020-06-29 |  |  | 15 | 20%
4.2 | Functional Description | IC Pro | 2020-06-19 | 2020-06-29 |  |  | 11 | 0%
4.3 | FAT Procedure | IC Pro | 2020-07-20 | 2020-07-24 |  |  | 5 | 0%
4.4 | Installation Commisioning Plan | IC Pro | --- | --- |  |  | 2 | 0%
4.5 | SAT Procedure | IC Pro | --- | --- |  |  | 5 | 0%
4.6 | Operational & Maintenance Manual | IC Pro | --- | --- |  |  | 5 | 0%
5 | Documents Approval | --- | 2020-06-10 | 2020-07-04 | --- |  | 5 | 0%
5.1 | Project Plan | CustomerName | 2020-06-10 | 2020-06-12 |  |  | 3 | 100%
5.2 | Control BOM | CustomerName | 2020-06-19 | 2020-06-22 |  |  | 4 | 0%
5.3 | Electrical BOM | CustomerName | 2020-06-25 | 2020-06-28 |  |  | 4 | 0%
5.4 | Datasheets | CustomerName | 2020-06-19 | 2020-06-22 |  |  | 4 | 0%
5.5 | Panel GA/IGA Drawings | IC Pro | 2020-06-25 | 2020-06-28 |  |  | 4 | 0%
5.6 | Electrical Panel Drawings | IC Pro | 2020-06-30 | 2020-07-04 |  |  | 5 | 0%
5.7 | Functional Description | CustomerName | 2020-06-30 | 2020-07-03 |  |  | 4 | 0%
5.8 | FAT Procedure | CustomerName | 2020-07-25 | 2020-07-29 |  |  | 5 | 0%
5.9 | SAT Procedure | CustomerName | --- | --- |  |  | 3 | 0%
6 | Purchase | --- | 2020-06-25 | 2020-07-19 | --- |  | 25 | 0%
6.1 | Control System Purchase | IC Pro | 2020-06-25 | 2020-07-19 |  |  | 25 | 0%
6.2 | Electrical System Purchase | IC Pro | 2020-06-29 | 2020-07-18 |  |  | 20 | 0%
7 | Manufacturing | --- | 2020-07-15 | 2020-07-24 | --- |  | 10 | 0%
7.1 | Panel Manufacturing | IC Pro | 2020-07-15 | 2020-07-24 |  |  | 10 | 0%
8 | PLC and SCADA Development | --- | 2020-06-29 | 2020-07-23 | --- |  | 25 | 0%
8.1 | PLC Programming | IC Pro | 2020-06-29 | 2020-07-23 |  |  | 25 | 0%
8.2 | SCADA Programming | IC Pro | 2020-06-29 | 2020-07-23 |  |  | 25 | 0%
9 | Internal FAT | --- | 2020-07-27 | 2020-08-05 | --- |  | 10 | 0%
9.1 | Internal Testing | IC Pro | 2020-07-27 | 2020-08-05 |  |  | 10 | 0%
10 | FAT | --- | 2020-08-10 | 2020-08-14 | --- |  | 5 | 0%
10.1 | FAT | IC Pro/CustomerName | 2020-08-10 | 2020-08-14 |  |  | 5 | 0%
11 | Shipment to Site | --- | 2020-08-15 | 2020-08-19 | --- |  | 3 | 0%
11.1 | Packing | IC Pro | 2020-08-15 | 2020-08-17 |  |  | 3 | 0%
11.2 | Shipping | IC Pro | 2020-08-18 | 2020-08-19 |  |  | 2 | 0%
Formulas:
PLANNED START = MIN([PLANNED START, row below])
PLANNED START = MIN([PLANNED START, row below]:D11)
PLANNED END = MAX([PLANNED END, row below])
PLANNED END = IF(ISBLANK([PLANNED START])," - ",IF([DAYS]=0,[PLANNED START],[PLANNED START]+[DAYS]-1))