## Frontpage
Project Code Project Name Questionnaire
ISSUED FOR REVIEW |  | A |  | 07.09.2020 | ANP | UDHY | VAITHI
REASON FOR ISSUE |  | REVISION |  | REV. DATE | PREP. BY | CHECKED | APPROVED
|  |  | Document Family: |  | LIST |  | No. of pages:
2
Project: | XXXXXX
Location | Location
Client: | Client Name
Document Title: Project Questionnaire
Client Doc. No: |  |  | Doc. No.: |  |  |  | Rev. :
|  |  | ICP_PR_XXXX_ProjectName_PQD_DDMMMYYY |  |  |  | A

## Questions
Q&A LIST
Log No | Item | Description/Questions ? | Raise by [Who] | Date Raised | Reply | Answered By | Date Shared
1 | - | Master PLC contain both filling and analysis? | Anoop | 2019-08-26 | Master PLC is a filling PLC, which sends only the control signal to analysis plc to start anlysis process | Customer | 2019-08-27
2 | - | Important milestones to be met | Anoop | 2019-08-26 | FAT, Delivery, Commissioning | Vaithi | 2019-08-27
3 | - | HMI is in the remote panel? | Anoop | 2019-08-26 | HMI is at the filling panel | Murali | 2019-08-27
4 | - | Valve, transmitter, solenoid valve supplied by? | Anoop | 2019-08-26 | Vendor to supply solenoid valve | Customer | 2019-08-27
5 | - | What is the plc brand for cryogenic pump | Anoop | 2019-08-26 | Siemens | Customer | 2019-08-27
6 | - | No. of IO modules | Anoop | 2019-08-26 | Vendor to calculate and come up with the proposal | Customer | 2019-08-27
7 | - | Every HMI will have one barcode scanner? | Anoop | 2019-08-26 | Yes | Customer | 2019-08-27
8 | - | Tight timeline from PO to FAT, require 12 weeks | Anoop | 2019-08-26 | Vendor to submit their sechulded time line from PO approval to Handover to ALsg | Customer | 2019-08-27